## Plan
Items | Sprint Goal | Complete
Training Documentation - Set up training plan and documentation for Dev team | Sprint 45
Main Menu and App | Sprint 46
Main Menu Filter | Sprint 46
Comparison Screen | Sprint 46
Dashboard Toolbar | Sprint 47
Dialog | Sprint 47
Grid and Cell level Editing | Sprint 48
Side Panel - Navigating through all panels ie properties panel and account etc | Sprint 48
Tree | Sprint 49
Cross Reference | Sprint 49
Accessibility training to be issued in a timely manner to all devs with deliverables in order to get them up to speed

## Main Menu and App Bar
Issue | Status | Tested Internally | Complete
Loses focus for a while after Tabbing on the Assist icon. It seems to be focused in the middle of the screen on hidden objects | Done
Esc should close the menu and focus on the button | Done
If on the menu and you click tab and focus goes to the main content, then menu should close. | Done
Possibility to have the screen reader list oh many items or where you are in the list. Ie 1 of 12 | Done
Rename Button label to menu | Done
When the menu is open, Tab opens the filter. Pressing Tab again should activate the menu list, then up and down should navigate each item | Done
Rename roles to menuitems | Done
The menu attributes are currently on the wrong container | Done
Need to override default shortkeys to open the menu (Might be in the shortcut manager) | Done
While using screen reader commands to scroll (ctl + opt or alt + right arrow), the user is not able to go to the sub menu items, instead the whole menu closes. The browser focus is still on the main menu button. | Done
Latest User Test Result | Status
There were a few issues as documneted above when testing with Cornelia. | Needs Retesting

## Main Menu Filter
Issue | Status | Tested Internally | Complete
Filter reads as an input. Need to add role=”search” | Done
Dropdown in the filter list does not read back through the screen reader | Done
The filter should order the items by typed word followed by specificity. Ex resource. | Done
Latest User Test Result | Status
There were a few issues as documneted above when testing with Cornelia. | Needs Retesting

## Dashboard Toolbar
Issue | Status | Tested Internally | Complete
Filter reads as an input. Need to add role=”search”
Properties Panel Button – when accessing the properties panel, the focus should be on the first item.
Query builder button - focus stays on the button and doesn’t move to the active dialog. Esc should close this
View button – focus moves to the first item but cant get back to close the button quickly again with out having to follow the tab sequence. Esc to close the window
New Button – When opening the new crud, the voice assist stays on the dashboard toolbar button. Focus should be on the first input in the crud.
Exiting the panel should then bring you back to the toolbar button that opened the panel.
Esc doesn’t close anything
Keyboard shortcuts need to be added for quick reference

## Dialog - Crud
Issue | Status | Tested Internally | Complete
When closing the dialog, focus should fall on the item that opened it | Done
Tab group header aren’t navigable. Should be able to navigate using left and right. Tab again to move out of the group of tabs. | Done
Need keyboard shortcuts to scroll through tabs so the user doesn’t have to scroll to the top of the page in order to go to the next tab (Ctrl s+ Shift + 1 to 9)
When closing a look up again the focus should be on the item that opened it. | Done
Look ups aren’t navigable (Grid issue)
When the dialog is open, items in the background should no longer be accessible. | Done

## Grid
Issue | Status | Tested Internally | Complete
Accessing the grid first it focuses on the checkbox in the table header then pressing tab the whole grid is highlighted when you focus on it. Should focus on the first cell.
The grid is not accessible with screen reader
Cant access the dialog from a cell when pressing enter.
Latest User Test Result | Status
There were a few issues as documneted above when testing with Cornelia. | Needs Retesting

## Side Panel
Issue | Status | Tested Internally | Complete
Currently set up as tabs - Tab once to access tab headings. Then press up or down to navigate the tabs. Tab again to activate the tab pane and focus on the first item.

## Tree
Issue | Status | Tested Internally | Complete
Can’t access tree with only keyboard.
Enter should bring up the dialog box.
Spacebar to select

## Cross Ref
Issue | Status | Tested Internally | Complete
On dialog opening the focus should be on the first input field

## Comparison Screen
Issue | Status | Tested Internally | Complete
On dialog opening the focus should be on the first input field